## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Plan and bootstrap | 3 | 2024-07-14 | Created initial project and personal template files. Made planning and architectural decision.
Splash screen - launcher icon | 1.5 | 2024-07-16 | Completed the implementation of the splash screen and launcher icon
User story 2 completed | 12 | 20-21.07.2024 | Completed location, search, house feed, ordering houses, animations for detail screen and localization. House fetching and business logic unit tests
User story 3 completed | 5 | 2024-07-21 | Everything explained on story 3 implemented such as map, house detail, and url launchers.
User story 4 completed | 3 | 2024-07-21 | Made design, and link
Total amount of hours | 24.5